**2. Communication and Engagement Plan**

**Planning Proposal for** Click or tap here to enter text.

Applicable Land: Click or tap here to enter text.Insert Property Description

Applicant: Click or tap here to enter text.

On behalf of: Click or tap here to enter text.

|  |  |
| --- | --- |
| **Template** | **What is covered?** |
| 1. **Project Overview** | This document provides information on the Planning Proposal background, scope of works, project program (milestones) and risk management. |
| 1. **Communications Plan** | This document details key messages, stakeholders and communication mechanisms at different stages of the planning process. |
| 1. **Probity Plan** | This document provides information on project governance, probity management and procedures. |
| 1. **Fee Agreement** | This document sets out the contract agreement for Council to undertake precinct planning at full cost recovery. |

**Table of Contents**

[Abbreviations 4](#_Toc182918055)

[Definitions 5](#_Toc182918056)

[1. Introduction 7](#_Toc182918057)

[1.1 Background 7](#_Toc182918058)

[1.2 Purpose of the Plan 10](#_Toc182918059)

[2. Key Messages 10](#_Toc182918060)

[2.1 Key Messages 10](#_Toc182918061)

[3. Stakeholder Identification and Analysis 12](#_Toc182918062)

[3.1 Stakeholder Identification 12](#_Toc182918063)

[Table 1 – Potential Stakeholders and Consultation Approaches 13](#_Toc182918064)

[4. Communication and Engagement Plan 15](#_Toc182918065)

[4.1 Plan Overview 15](#_Toc182918066)

[4.2 Communication and Engagement Strategy 16](#_Toc182918067)

[4.3 Initial Notification (Prior to Endorsement) 16](#_Toc182918068)

[4.4 Assessment (Prior to Gateway) 17](#_Toc182918069)

[4.5 Public Exhibition (Pending Council Endorsement) 17](#_Toc182918070)

[4.6 Post Exhibition 18](#_Toc182918071)

# Abbreviations

|  |  |
| --- | --- |
| Camden PCG | Camden Precinct Collaboration Group |
| CP | Section 7.11 Contribution Plan |
| DCP | Development Control Plan |
| DPHI | NSW Department of Planning, Housing and Infrastructure |
| EP&A Act | NSW Environmental Planning and Assessment Act 1979 |
| GSC/GCC | The former NSW Greater Sydney Commission/Greater Cities Commission |
| ILP | Indicative Layout Plan |
| LGA | Local Government Area |
| LEP | Local Environmental Plan |
| PCG | Project Control Group |
| PWG | Project Working Group |
| s7.11 | Section 7.11 of the EP&A Act |
| SEPP | State Environmental Planning Policy |
| SINSW | School Infrastructure New South Wales |
| SWGA | South West Growth Area |
| VPA | Voluntary Planning Agreement |

# Definitions

|  |  |
| --- | --- |
| **Term** | **Definition** |
| **Project Specific** | |
| Applicant | Refers to the person responsible for submitting the Planning Proposal onto the NSW Planning Portal. This may be the Proponent or may be the Lead Consultant. |
| Council Consultant | Refers to any specialist consultant engaged by Council to provide technical advice, undertake studies, create maps and drawings, prepare reports or any other work associated with the Proposal. |
| Planning Proposal | Refers to the Planning Proposal put forward to Council by the Proponent. |
| Precinct | Refers to land applying to the Planning Proposal as identified in **Figure 1.** |
| Project | Refers to the review and implementation of the Planning Proposal. |
| Project Control Group (Precinct PCG) | Comprises the Council Project Manager, Team Leader Strategic Planning, Manager Strategic Planning and may include senior management staff of Council (as required); and members of other NSW Government agencies (as required). |
| Project Manager | Refers to Council’s Strategic Planner, who is responsible for project managing the assessment of the Planning Proposal. |
| Project Participants | Refers to all Council officers and consultants involved in the preparation and assessment of the Planning Proposal including but not limited to: Project Manager, relevant Team Leaders, and Managers, Specialist Council officers, Council Consultants. |
| Project Working Group (PWG) | Comprises the Council Project Manager and Project Officers, Team Leader Strategic Planning and may include senior management staff of Council; the Proponent; key consultants (as required) and members of other NSW Government agencies (as required). |
| Proponent | Refers to person and/or company responsible for developing and financing the Planning Proposal. |
| Proponent’s Consultant | Refers to any specialist consultant engaged by the Proponent to provide technical advice, undertake studies, create maps and drawings, prepare reports or undertake any other work associated with the Planning Proposal. |
| Lead Consultant (if applicable) | Refers to the main consultant contact for the Project (listed on the front page of this plan) who is acting on behalf of the Proponent and where applicable, may be the listed applicant for the Project on the NSW Planning Portal. |

|  |  |
| --- | --- |
| **General** | |
| Agencies | Government departments and public authorities who have a role in the review and assessment of a planning proposal. |
| Camden Local Planning Panel (CLPP) | Camden's Local Planning Panel (CLPP) is a panel of three independent expert members and a community member who provide advice to Council on Planning Proposals. LPPs are mandatory in Greater Sydney under the EP&A Act and are intended to ensure that decisions are made on technical merits, efficiency, fairness, and transparency, with the added benefit of local knowledge. |
| Camden Precinct Collaboration Group (Camden PCG) | Comprises representatives from Council executive and management teams, DPHI and representatives from other State agencies involved in precinct planning and delivery of infrastructure in the Camden Growth Areas. *Note: If the Camden PCG ceases or is not operational, support from DPHI will be sought to facilitate the same outcome.* |
| Camden LEP | Refers to the Camden Local Environmental Plan 2010 |
| Consultant | Refers to a matter specialist who provides expert professional advice, undertakes investigations and prepares reports in relation to a Planning Proposal. A consultant can be engaged by either Council or the Proponent. |
| Council | Refers to means Camden Council through its Council officials and/or any person authorised to act on Council’s behalf. |
| Council officer | Refers to members of Council staff and Council consultants, contractors and committee members but does not include the Elected Council. |
| Council official | Refers to a Council officer or member of the Elected Council. |
| DPHI | Refers to the NSW Department of Planning, Housing and Infrastructure. |
| Elected Council | Refers to the Councillors of Council. |
| Department or DPHI | Refers to the NSW Department of Planning, Housing and Infrastructure. |
| Fee Agreement | Refers to a signed agreement for Council to assess a Significant Planning Proposal at full cost recovery in accordance with Councils Fees and Charges. |
| Land Owner | Refers to the person(s), company, agency or organisation that owns land within the Precinct. who may initiate, provide consent to, or be a key stakeholder in the Project. |
| Precincts SEPP | Refers to *State Environmental Planning Policy (Precincts – Western Parkland City) 2021.* |
| Master-Planner | Refers to the Council appointed consultant to assist with the detailed master planning of the precinct. |

# Introduction

## 1.1 Background

A Significant Planning Proposal (the Project) has been submitted to Council for assessment. The Project site is within the South West Growth Area (SWGA) with the location of the Project shown in **Figure 1**.

In November 2019, the Minister announced a new approach to Precinct Planning in New South Wales, comprising of four (4) precinct pathways as shown in **Figure 2** below.

Under the new approach, the remaining precincts within the SWGA have been identified under a ‘collaborative planning’ pathway, allowing precinct planning to be progressed via a Planning Proposal lodged with Council.

Precinct planning is required prior to the land being rezoned and broadly includes:

* Project managing the Planning Proposal to provide a statutory plan and detailed development control plan;
* Coordinating infrastructure provision and agency requirements, including establishing funding arrangements; and
* Achieving Precinct level approval for relevant integrated development and other statutory requirements.

****

Figure 1: Land Subject to the Project

To guide planning, the DPHI released an updated Structure Plan for the South West Growth Area (SWGA) and a Guide to the South West Growth Area in December 2022.

A Section 9.1 Ministerial Direction has also been issued to support the SWGA. This Direction requires planning proposals to demonstrate consistency with the 2022 Structure Plan and Guide.




Figure 2: New Approach to Precinct Planning (Source: DPE, 2019)

Camden Council is also responsible for considering proposals to amend the Camden Local Environmental Plan 2010, which applies to land located outside of the South West Growth Area.

All Planning Proposals need to be prepared in accordance with the Department of Planning, Housing and Infrastructure’s (DPHI’s) Local Environmental Plan (LEP) Making Guideline, relevant 9.1 Directions, State Environmental Planning Policies as well as regional, district and local plans and policies.

Proposals within the SWGA also need to be in accordance with the South West Growth Area Structure Plan and Guideline.

All Planning Proposals within the Camden Local Government Area must be in accordance with the Camden Planning Proposal Policy and Procedure and all Community engagement activities undertaken as part of a Planning Proposal must be developed in accordance with the Camden Community Participation Plan.

## 1.2 Purpose of the Plan

This Communication and Engagement Plan has been prepared to:

* Identify the key stakeholders of the Project;
* Provide a guide to engaging and informing key audiences during the precinct planning process;
* Establish the key communication objectives for the Project;
* Detail the key modes of communication at different stages throughout the assessment of the Project; and
* Determine the agreed messaging for both Council and Proponent led community engagement activities.

The Communication and Engagement Plan has been prepared to be consistent with Council’s Community Participation Plan (CPP).

The Communication and Engagement Plan will be updated regularly to reflect any changes to the Project as assessment progresses.

# Key Messages

## 2.1 Key Messages

The key messages to be communicated include the following:

Insert any key messages to be communicated to the community and these may include some or all of the following examples:

* The location of the Project is shown in Figure 1.
* The Precinct ([Insert ha]) will facilitate approximately [Insert no. dwellings] dwellings to accommodate an expected population of [Insert no. residents] residents.

Note: The total number of dwellings and people have been identified by the Proponent and are subject to detailed review/assessment by Council officers.

* The precinct will provide the services that are required for residents and the new community, including:
  + a neighbourhood centre;
  + public open space;
  + riparian corridors;
  + walking and cycling paths;
  + public transport connections, and
  + other required community infrastructure as determined through the assessment of the Project.
* The Precinct will provide diversity in housing typologies and greater choice of housing types for the future community.
* The Precinct will be highly connected, with convenient access to public transport, public open spaces, facilities and amenities.
* The Precinct will celebrate its natural environment through conservation of trees and riparian corridors and will create a sustainable place which addresses m urban heat, promotes resilience to climate change, and encourages an active, healthy and engaged community.
* Existing landowners and surrounding owners within the Precinct will be offered opportunities to provide input into the precinct planning process.
* The precinct planning process will be independent, transparent and free of bias.

# Stakeholder Identification and Analysis

## 3.1 Stakeholder Identification

Stakeholders are identified as individuals or groups of people who may be affected by the outcome of the Project. A list of potential stakeholders is provided in Table 1.

The Communication and Engagement Plan will be tailored to ensure that all audiences/stakeholders are adequately consulted at the relevant stages of the Project.

The following section provides an analysis of each potential stakeholder, their level of interest/power and the method of consultation required for each stakeholder.

A diagram of a diagram

Description automatically generated with medium confidence

## Table 1 – Potential Stakeholders and Consultation Approaches

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Potential Stakeholder** | **Power/Interest** | **Method/Type of Consultation** | **Frequency** | **Responsibility** |
| Camden Council Officials (including Council Officers and Councillors) | Process owner | Inform/consult | Ongoing | Responsible for decision making and delivery of rezoning. |
| Landowners (public and private, including landowner organisations) | Medium/ Medium | Inform/consult | Ongoing | May initiate, provide consent to, or be a key stakeholder whose interests need to be considered in the precinct planning process. |
| Proponent/ Proponent Consultant | Medium/High | Inform/consult | Ongoing | Initiates and assists in the precinct planning process. |
| Camden PCG | Critical | Involve/consult/  collaborate | Ongoing | Responsible for coordinating timing, servicing of infrastructure, and addressing blockages/delays in the process.  If the Camden PCG ceases or is not operational, assistance from DPHI will be sought to facilitate the same outcome. |
| PCG | Critical | Involve/consult/  collaborate | Ongoing | Responsible for overseeing the assessment of the Project |
| DPHI | Critical | Involve/consult/  collaborate | Ongoing | Responsible for finalisation of the SEPP amendment. . |
| NSW Government Agencies and service providers (e.g. Sydney Water) | Critical | Involve/consult/  collaborate  (i.e. Camden PCG or alternative arrangement) | Ongoing | Responsible for confirming timing of/and delivery of servicing infrastructure. |
| Aboriginal and Torres Strait Islander Communities | Medium/High | Inform/consult | During/ post initial notification and public exhibition, - in the preparation of any Aboriginal Cultural Heritage Assessment and in addressing Connecting to Country requirements. | Identifying potential for impact on cultural traditions and beliefs, cultural use of the land and any archaeological artefacts on the site. |
| Adjoining/ nearby landowners | Medium | Inform/consult | Ongoing | May be affected by future development of the precinct; inform the precinct planning process. |
| Submitters (during initial notification and public exhibition stage) | Medium | Inform/consult | During/ post initial notification and public exhibition | Inform the precinct planning process; may be affected by future development of the precinct. |
| Community | Low | Inform | As needed | May be affected by future development of the precinct. |
| Local, State and Federal MPs | High | Inform/consult | Ongoing | Responsible for addressing/  managing community concerns. |
| Council Committees | Medium/High | Inform/consult | As needed | Provide advice on matters relevant to the committee; inform the precinct planning process. |

# Communication and Engagement Plan

## 4.1 Plan Overview

|  |
| --- |
| **Insert Name of Project** |
| Introduce and provide a background to the project. |

|  |
| --- |
| **Overview of the Project** |
| Provide an overview of the project. |

|  |
| --- |
| **Planning Proposal Package** |
| The planning proposal package includes the following:   * Click or tap here to enter text. |

|  |
| --- |
| **Camden’s Community Participation Plan** |
| Camden Council’s Community Participation Plan encourages open and inclusive, easy, relevant, timely and meaningful opportunities for community participation. The community will have the opportunity to comment on proposed changes during the public exhibition period. |

|  |
| --- |
| **Stakeholders** |
| The people likely to be most interested in or affected by the project can be broadly described as:   * Click or tap here to enter text. |

|  |
| --- |
| **Communication and Engagement Plan** |
| Consideration has been given to the likely interest and needs of stakeholders prior to preparing a Communication and Engagement Plan for the project.  A more detailed Communication and Engagement Plan will be prepared to identify tasks, specifically scope individual stakeholder needs and develop the associated engagement material. |

## 4.2 Communication and Engagement Strategy

These six pillars guide all communication and engagement activities delivered by Council.

A diagram of a diagram

Description automatically generated with medium confidence

## 4.3 Initial Notification (Prior to Endorsement)

|  |  |  |
| --- | --- | --- |
| **Summary** | | |
| The main priorities of the pre-exhibition consultation is to:   * Seek input from government agencies; * Seek feedback from local landowners, adjoining landowners; * Engage with internal staff, Councillors and the Project Working and Control Groups to finalise the draft Planning Proposal; and * Finalise Council’s Communication and Engagement approach for Public Exhibition and beyond.   Consider the level of interest and needs of stakeholders during this phase of the project is provided in the table below. | | |
| **Communication** | **Engagement** | **Key Stakeholders** |
| * Project Working Groups and Meetings * Project Control Group * Camden PCG * Councillor briefing * Council Report * Letters and/or e-mail and/or telephone call * Click or tap here to enter text. | * Internal feedback. * DPHI feedback. * Other agency feedback. * Councillor feedback. * Landowner feedback. * Click or tap here to enter text. | * Camden Council Councillors * Council Officers * Land Owners * DPHI and other government agencies * Click or tap here to enter text. |

## 4.4 Assessment (Prior to Gateway)

|  |  |  |
| --- | --- | --- |
| **Summary** | | |
| The main priorities of the assessment stage is to update the community and key stakeholders on key project milestones (i.e. outcomes of initial notification, Local Planning Panel and Council meetings). | | |
| **Communication** | **Engagement** | **Key Stakeholders** |
| * Project Working Groups and Meetings * Project Control Group meetings and updates * Camden PCG/DPHI meetings and updates * Councillor briefing * Camden Local Planning Panel Report * Council Report * Newsletter * Letters and/or e-mail * One on one meetings * Click or tap here to enter text. | * Internal feedback. * LPP feedback. * Councillor feedback. * DPHI feedback. * Other agency feedback. * Landowner/stakeholder feedback. * Click or tap here to enter text. | * Camden Council Councillors * Council Officers * DPHI * LPP * Government agencies * Master Planner * Proponent * Proponent Consultant * Click or tap here to enter text. |

## 4.5 Public Exhibition (Pending Council Endorsement)

|  |  |  |
| --- | --- | --- |
| **Summary** | | |
| **Number of weeks on exhibition:** Click or tap here to enter text.  The main priority of the public exhibition stage is to provide further opportunities to engage with the community to inform and guide finalisation of the Precinct. During the public exhibition period, the Project Package will include:   * Project Overview; * Frequently Asked Questions (FAQ); * Draft Planning Proposal; * Draft Indicative Layout Plan (ILP); * Draft Development Control Plan (DCP); * Supporting technical studies and mapping; and * Click or tap here to enter text. | | |
| **Communication** | **Engagement** | **Key Stakeholders** |
| * Councillor briefing (if required). * Councillor update. * Fact and FAQ sheet (including contact details for translation service on back of letter). * Referrals to relevant State Government Agencies. * Social Media. * Online interactive material including FAQ. * Resources on display at all libraries and customer service. * Letters and/or e-mails * Click or tap here to enter text. | * Your Voice Camden project page updated to host (in addition to above) Draft DCP and submission page. * Subscriber notification of exhibition. * Referral via the NSW Planning Portal. * Document display at libraries and Council administration building etc. * One on one meetings with landowners/stakeholders (if required). * Click or tap here to enter text. | * Camden Council councillors and staff. * Residents including landowners * Government agencies and authorities * Aboriginal and Torres Strait Islander Communities * General public via Your Voice Camden and media/social media * Master Planner * Click or tap here to enter text. |

## 4.6 Post Exhibition

|  |  |  |
| --- | --- | --- |
| **Summary** | | |
| The main priority of the post exhibition stage is to:   * Provide an update on the outcomes of the planning process; * Review and respond to submissions received during the public exhibition period; * Refine the final Planning Proposal package and draft DCP in response to submissions (if required); * Further collaborate with State Agencies (if required); * Prepare a report for Council, summarising and responding to submissions received during public exhibition (if required); * Prepare and send the Planning Proposal to DPHI for finalisation; and * Adopt the DCP (if required). | | |
| **Communication** | **Engagement** | **Key Stakeholders** |
| * Councillor briefing (if required). * Council report (if required). * Acknowledge submissions. * Notification of adoption of the SEPP amendment and DCP to submitters and in Councillor update. * Click or tap here to enter text. | * Your Voice Camden project page updates. * Clarify submissions where required (potentially conduct meetings, phone calls etc.). * Letters and/or e-mails. * Click or tap here to enter text. | * Camden Council councillors * Council Officers * Proponent * Proponent Consultant * Engagement consultant. * Your Voice Camden project followers * Submission makers * Government agencies * DPHI * Master Planner * Click or tap here to enter text. |